## Summary
Nima - 48 Hour Operational Audit
30 July 07:00 to 1 August 07:20 UTC ¦ every n8n execution reviewed ¦ prepared 1 Aug 2026
VOLUME
Total n8n executions in 48h | 4,357 across 13 workflows
Executions that ended in error | 46
Conversations handled by the assistant | 81 turns
of which real clients | 21 turns from 8 unique clients
of which testers / internal | 60 turns
Outbound WhatsApp messages attempted | 127
THREE INCIDENTS IN 48 HOURS
1. Live assistant broken by a bad deploy | 30 Jul 12:56 to 15:45 (2h49m). 5 conversations received NO reply at all. Cause: invalid code deployed straight to live without a test run.
2. Booking confirmation card sent wrong information | 31 Jul 15:09 to 1 Aug 06:48. 62 clients received a confirmation. 19 of them were for appointments ALREADY IN THE PAST. Reschedules were ignored entirely, so any client whose booking moved now holds the wrong date.
3. WhatsApp connection lost | 1 Aug 04:37, still down. Device removed / 401 conflict. Nima cannot send OR receive. Reception receives no missed-call alerts.
CLIENT IMPACT
Clients holding a confirmation message | 62 delivered (56 unique numbers)
Confirmations for appointments already past | 19 - these clients were told an appointment was 'confirmed' days after it happened
Confirmations that never arrived | 16 - failed at the WhatsApp gateway
Reschedule events silently discarded | 272 of the 350 Zenoti events were ignored by design (updates, cancellations, status changes)
Clients who got no reply during the outage | 5 conversations, 3 of them real clients
CURRENT STATE
Booking confirmation card | OFF. Workflow deactivated, endpoint returns 404. Verified.
Live assistant (Nima) | Code is healthy, but UNREACHABLE while WhatsApp is disconnected
Outbound automations that can reach a client | NONE. All remaining senders are hardcoded to reception or Younes.
WhatsApp connection | DOWN since 1 Aug 04:37. Needs a QR rescan on the Niumee phone.

## All Workflows (48h)
Workflow | Active | Executions | Errors | Note
WF-MissedCall Poller v2 (Cloud) — ACTIVATE after firewall opens | Yes | 2901 | 0
WF-Zenoti Webhook (Appointments) | No | 350 | 16 | THE INCIDENT. Now deactivated.
TEMP PBX Open Notifier — delete after migration | Yes | 290 | 0
WF-MissedCall Watchdog | Yes | 290 | 1
WF-Bot-Availability | Yes | 130 | 0
WF-GUARD Guarded Send | Yes | 127 | 19 | All outbound WhatsApp passes through here. 19 failures = the connection outage.
Niumee AI Receptionist v3 (State Machine) - TEST | Yes | 97 | 0 | My acceptance testing. Never faced a real client.
Niumee AI Receptionist v2 (Supabase) - LIVE | Yes | 81 | 5 | The live assistant. 5 errors = the 30 Jul bad deploy.
WF-MissedCall Recovery | Yes | 42 | 2
Niumee AI Receptionist v2 - TEST COPY (21 Jul) | Yes | 34 | 2
WF-Zenoti-Price-Search (fallback backend) | Yes | 7 | 1
WF-Bot-History | Yes | 6 | 0
ASTRA - Niumee L1 Daily Load Sync | Yes | 2 | 0

## Confirmations Delivered
Sent (UTC) | Client number | Appt date | Message | Flag
2026-07-31 15:26:46 | 35679313906 | 2026-08-03 | Hi Miriam, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 03/08/2026 ¦ Time: 11:15 ¦ Service: Brow architecture - Threading with Magda Strus ¦ ¦ To reschedule, simply reply to this message. | check against current Zenoti booking
2026-07-31 15:27:37 | 35699017313 | 2026-08-01 | Hi Laura, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 01/08/2026 ¦ Time: 12:00 ¦ Service: Accure Acne Treatment Consultation with Jamie Elizabeth Castillo ¦ ¦ To reschedule, simply reply | check against current Zenoti booking
2026-07-31 15:38:04 | 35679835250 | 2026-09-11 | Hi Steve, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 11/09/2026 ¦ Time: 16:30 ¦ Service: Laser - Genital Area (Male) and Buttocks by Nurse with Liza Montalbo ¦ ¦ To reschedule, simply r | check against current Zenoti booking
2026-07-31 15:38:47 | 35699654627 | 2026-08-04 | Hi Magdalena, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 04/08/2026 ¦ Time: 18:30 ¦ Service: Dermapen + Exosomes treatment Full face & eyes with Jamie Elizabeth Castillo ¦ ¦ To reschedu | check against current Zenoti booking
2026-07-31 15:55:53 | 35679540754 | 2026-08-01 | Hi Alejandra, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 01/08/2026 ¦ Time: 13:15 ¦ Service: Sculptpro Free Consultation & Trial session with Liza Montalbo ¦ ¦ To reschedule, simply rep | check against current Zenoti booking
2026-07-31 15:58:58 | 35699467604 | 2026-08-04 | Hi Gertrude, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 04/08/2026 ¦ Time: 12:00 ¦ Service: Highlights-half head/crown by Hair Stylist-ServicingTime with Aaron Micallef ¦ ¦ To reschedul | check against current Zenoti booking
2026-07-31 16:51:12 | 35679263774 | 2026-09-04 | Hi Abigail, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 04/09/2026 ¦ Time: 09:00 ¦ Service: Gel Polish (feet) Gelish (Soak,Scrub, Gelish) with Aishah Nabagereka ¦ ¦ To reschedule, simply | check against current Zenoti booking
2026-07-31 16:55:40 | 35699455059 | 2026-08-19 | Hi Rachel, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 19/08/2026 ¦ Time: 11:30 ¦ Service: Keratin Phase 2 (CocoChoco) with Jan Nguyen ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ N | check against current Zenoti booking
2026-07-31 17:01:04 | 35679539243 | 2026-08-01 | Hi Amy, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 01/08/2026 ¦ Time: 09:00 ¦ Service: Blow Dry Medium - by Hair Stylist with Tyrah Teopista ¦ ¦ To reschedule, simply reply to this mess | check against current Zenoti booking
2026-07-31 17:25:05 | 35679457345 | 2026-08-04 | Hi Sabrina, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 04/08/2026 ¦ Time: 14:30 ¦ Service: Brow architecture - Threading with Melanie Scibberras ¦ ¦ To reschedule, simply reply to this | check against current Zenoti booking
2026-07-31 17:46:14 | 35679896428 | 2026-08-08 | Hi Jake, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 08/08/2026 ¦ Time: 16:15 ¦ Service: PRP Hair stimulation - single with Lawrence Calleja ¦ ¦ To reschedule, simply reply to this messa | check against current Zenoti booking
2026-07-31 17:48:13 | 35677207603 | 2026-07-31 | Hi Queenie, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 31/07/2026 ¦ Time: 19:15 ¦ Service: Laser Card - 15 mins redeemable session with Liza Montalbo ¦ ¦ To reschedule, simply reply to | check against current Zenoti booking
2026-07-31 17:56:07 | 35699479623 | 2026-08-07 | Hi Jeanette, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 07/08/2026 ¦ Time: 17:00 ¦ Service: CelluSmooth 1-Hour Session ( Two Areas ) with Liza Montalbo ¦ ¦ To reschedule, simply reply t | check against current Zenoti booking
2026-07-31 17:59:57 | 35699422404 | 2026-07-31 | Hi Denise, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 31/07/2026 ¦ Time: 19:45 ¦ Service: Hair Loss Consultation with Lawrence Calleja ¦ ¦ To reschedule, simply reply to this message. ¦ | check against current Zenoti booking
2026-07-31 18:01:43 | 35699292900 | 2026-07-31 | Hi Gilbert, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 31/07/2026 ¦ Time: 20:30 ¦ Service: Hair Loss Consultation with Lawrence Calleja ¦ ¦ To reschedule, simply reply to this message. | check against current Zenoti booking
2026-07-31 18:09:20 | 35699292900 | 2026-07-31 | Hi Gilbert, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 31/07/2026 ¦ Time: 20:30 ¦ Service: Hair Loss Consultation with Lawrence Calleja ¦ ¦ To reschedule, simply reply to this message. | check against current Zenoti booking
2026-07-31 18:12:25 | 35699762383 | 2026-08-01 | Hi Francesca, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 01/08/2026 ¦ Time: 13:00 ¦ Service: Blow Dry Long - by Hair Stylist with Samuel Cilia ¦ ¦ To reschedule, simply reply to this me | check against current Zenoti booking
2026-07-31 18:29:50 | 35677453228 | 2026-08-03 | Hi Gabriella, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 03/08/2026 ¦ Time: 12:45 ¦ Service: Blow Dry Medium - by Hair Stylist with Tyrah Teopista ¦ ¦ To reschedule, simply reply to thi | check against current Zenoti booking
2026-07-31 20:08:24 | 35679790114 | 2026-08-04 | Hi Deborah, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 04/08/2026 ¦ Time: 14:45 ¦ Service: Blow Dry Short - by Hair Stylist with Samuel Cilia ¦ ¦ To reschedule, simply reply to this mes | check against current Zenoti booking
2026-07-31 21:08:02 | 35699990523 | 2026-08-01 | Hi Sara, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 01/08/2026 ¦ Time: 11:30 ¦ Service: Brow architecture - Threading with Magda Strus ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ | check against current Zenoti booking
2026-07-31 23:11:48 | 35679801305 | 2026-07-28 | Hi Steph, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 28/07/2026 ¦ Time: 18:30 ¦ Service: Laser Card - 15 mins redeemable session with Jamie Elizabeth Castillo ¦ ¦ To reschedule, simply | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:15:44 | 35679052083 | 2026-07-30 | Hi Nick, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 30/07/2026 ¦ Time: 12:00 ¦ Service: Hair Cut - Male with Alberto Spiteri ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee Med | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:19:45 | 35679035743 | 2026-07-29 | Hi Sarah, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 29/07/2026 ¦ Time: 16:30 ¦ Service: Hair Cut - by Director with Alberto Spiteri ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Ni | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:29:47 | 35699069286 | 2026-07-29 | Hi Chelly, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 29/07/2026 ¦ Time: 17:30 ¦ Service: Waxing - Eyebrow Tidy with Jessica Casha ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Nium | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:37:47 | 35699251060 | 2026-07-25 | Hi Corinne, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 11:15 ¦ Service: Natural nail mani with Mary Gorret Nabukeera ¦ ¦ To reschedule, simply reply to this message. ¦ | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:37:49 | 35677082149 | 2026-09-19 | Hi Charmaine, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 19/09/2026 ¦ Time: 08:00 ¦ Service: Laser card- 30 mins with Liza Montalbo ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niu | check against current Zenoti booking
2026-07-31 23:37:49 | 35699467286 | 2026-07-25 | Hi emma, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 09:00 ¦ Service: Brow architecture - Threading with Jessica Casha ¦ ¦ To reschedule, simply reply to this message. | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:41:44 | 35679040388 | 2026-08-08 | Hi Camille, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 08/08/2026 ¦ Time: 10:30 ¦ Service: Gel Polish (feet) Gelish (Soak,Scrub, Gelish) with Nashra Apad ¦ ¦ To reschedule, simply reply | check against current Zenoti booking
2026-07-31 23:51:45 | 35679477943 | 2026-07-28 | Hi Rose, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 28/07/2026 ¦ Time: 17:00 ¦ Service: Blow Dry Medium - by Hair Stylist with Jan Nguyen ¦ ¦ To reschedule, simply reply to this message | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:51:46 | 35679445015 | 2026-08-05 | Hi Dorianne, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 05/08/2026 ¦ Time: 09:30 ¦ Service: Infills with Frima Dag-o ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee Medical Aes | check against current Zenoti booking
2026-07-31 23:51:46 | 35699766266 | 2026-07-27 | Hi Nenita, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 27/07/2026 ¦ Time: 15:00 ¦ Service: Gel polish Mani (Gelish) with Nashra Apad ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niu | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:51:46 | 35699029137 | 2026-07-28 | Hi Nicole, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 28/07/2026 ¦ Time: 15:00 ¦ Service: Blow Dry Short - by Hair Stylist with Jan Nguyen ¦ ¦ To reschedule, simply reply to this messag | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:51:47 | 35699496090 | 2026-07-25 | Hi Mark, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 09:45 ¦ Service: Pain Management 30 min session with Stephen Moghrabi ¦ ¦ To reschedule, simply reply to this mess | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-07-31 23:53:46 | 35677090703 | 2026-08-08 | Hi Marthea, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 08/08/2026 ¦ Time: 11:45 ¦ Service: Electrolysis Face - 15 minutes with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply | check against current Zenoti booking
2026-07-31 23:53:47 | 35699427903 | 2026-07-25 | Hi Maria, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 09:45 ¦ Service: Waxing - Brazillian with Jessica Casha ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-08-01 00:09:49 | 35699453399 | 2026-08-13 | Hi Dolores, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 13/08/2026 ¦ Time: 13:15 ¦ Service: Hybrid Lashes-Touch Up with Magda Strus ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Nium | check against current Zenoti booking
2026-08-01 00:09:51 | 35699316633 | 2026-08-22 | Hi Ruzha, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 22/08/2026 ¦ Time: 13:30 ¦ Service: Infills with Frima Dag-o ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee Medical Aesthe | check against current Zenoti booking
2026-08-01 00:11:51 | 35679556877 | 2026-07-29 | Hi Dorothy, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 29/07/2026 ¦ Time: 14:30 ¦ Service: Botox- 50 units with Tyron Pillow ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee Med | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-08-01 00:11:51 | 35677315824 | 2026-07-28 | Hi Clyde, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 28/07/2026 ¦ Time: 09:30 ¦ Service: Hair Cut - Male with Jan Nguyen ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee Medical | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-08-01 00:11:52 | 35699812005 | 2026-07-25 | Hi Eleonor, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 11:45 ¦ Service: Sports therapy single session (45 min) with Stephen Moghrabi ¦ ¦ To reschedule, simply reply t | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-08-01 00:11:52 | 35699933097 | 2026-08-28 | Hi Ray, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 28/08/2026 ¦ Time: 12:30 ¦ Service: Laser card- 45 mins with Liza Montalbo ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee Me | check against current Zenoti booking
2026-08-01 00:13:48 | 35699961916 | 2026-09-23 | Hi Joanne, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 23/09/2026 ¦ Time: 18:00 ¦ Service: Gel Polish (feet) Gelish (Soak,Scrub, Gelish) with Aishah Nabagereka ¦ ¦ To reschedule, simply | check against current Zenoti booking
2026-08-01 00:15:47 | 35699946327 | 2026-08-13 | Hi Laura, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 13/08/2026 ¦ Time: 15:30 ¦ Service: Electrolysis Face - 15 minutes with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply to | check against current Zenoti booking
2026-08-01 00:15:47 | 35699726689 | 2026-08-08 | Hi Hannah, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 08/08/2026 ¦ Time: 10:00 ¦ Service: Laser Card - 15 mins redeemable session with Liza Montalbo ¦ ¦ To reschedule, simply reply to t | check against current Zenoti booking
2026-08-01 02:55:50 | 35679394737 | 2026-08-17 | Hi Joanna, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 17/08/2026 ¦ Time: 18:00 ¦ Service: UV Classic Lash infills with Magda Strus ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Nium | check against current Zenoti booking
2026-08-01 02:59:49 | 35679286382 | 2026-08-07 | Hi Jessica, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 07/08/2026 ¦ Time: 15:45 ¦ Service: Brow architecture - Threading with Melanie Scibberras ¦ ¦ To reschedule, simply reply to this | check against current Zenoti booking
2026-08-01 02:59:50 | 35679005661 | 2026-08-11 | Hi Luke, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 11/08/2026 ¦ Time: 18:00 ¦ Service: Hair Loss Consultation with Lawrence Calleja ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ N | check against current Zenoti booking
2026-08-01 02:59:50 | 35699585858 | 2026-08-29 | Hi Claire, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 29/08/2026 ¦ Time: 12:00 ¦ Service: Electrolysis Face - 30 minutes with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply t | check against current Zenoti booking
2026-08-01 02:59:50 | 35699585858 | 2026-08-22 | Hi Claire, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 22/08/2026 ¦ Time: 12:00 ¦ Service: Electrolysis Face - 30 minutes with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply t | check against current Zenoti booking
2026-08-01 02:59:50 | 35699585858 | 2026-09-05 | Hi Claire, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 05/09/2026 ¦ Time: 12:00 ¦ Service: Electrolysis Face - 30 minutes with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply t | check against current Zenoti booking
2026-08-01 03:09:50 | 35699860867 | 2026-07-25 | Hi Sue, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 13:45 ¦ Service: Blow Dry Short - by Hair Stylist with Tyrah Teopista ¦ ¦ To reschedule, simply reply to this messa | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-08-01 03:09:50 | 35699585858 | 2026-08-03 | Hi Claire, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 03/08/2026 ¦ Time: 15:30 ¦ Service: Electrolysis Face - 30 minutes with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply t | check against current Zenoti booking
2026-08-01 03:09:51 | 35699585858 | 2026-08-10 | Hi Claire, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 10/08/2026 ¦ Time: 15:30 ¦ Service: Electrolysis Face - 30 minutes with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply t | check against current Zenoti booking
2026-08-01 03:15:49 | 35699936235 | 2026-07-25 | Hi Keita, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 14:00 ¦ Service: Wash only with Alberto Spiteri ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee Medical | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-08-01 03:15:50 | 35679653088 | 2026-08-22 | Hi Jonathan, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 22/08/2026 ¦ Time: 11:00 ¦ Service: Hair Transplant Consultation with Nurse Lawrence Calleja ¦ ¦ To reschedule, simply reply to t | check against current Zenoti booking
2026-08-01 03:53:38 | 35679805984 | 2026-08-01 | Hi Marina, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 01/08/2026 ¦ Time: 09:00 ¦ Service: Blow Dry Long - by Hair Stylist with Tyrah Teopista ¦ ¦ To reschedule, simply reply to this mes | check against current Zenoti booking
2026-08-01 04:23:52 | 35699635522 | 2026-08-22 | Hi Svetlana, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 22/08/2026 ¦ Time: 08:30 ¦ Service: Facial - Elemis Touch Renew with Jessica Casha ¦ ¦ To reschedule, simply reply to this messag | check against current Zenoti booking
2026-08-01 04:23:52 | 35699241187 | 2026-08-08 | Hi Rosian, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 08/08/2026 ¦ Time: 12:15 ¦ Service: Electrolysis Face - 15 minutes with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply t | check against current Zenoti booking
2026-08-01 04:29:54 | 35679899667 | 2026-07-29 | Hi Lorna, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 29/07/2026 ¦ Time: 10:00 ¦ Service: Gehwol Herbal Pedicure & Polish with Natalia Dabrowska ¦ ¦ To reschedule, simply reply to this m | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-08-01 04:29:54 | 35699583259 | 2026-08-22 | Hi Shirley, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 22/08/2026 ¦ Time: 13:00 ¦ Service: Laser - Brazillian and UA by Nurse with Liza Montalbo ¦ ¦ To reschedule, simply reply to this | check against current Zenoti booking
2026-08-01 04:29:54 | 35679899667 | 2026-07-30 | Hi Lorna, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 30/07/2026 ¦ Time: 10:00 ¦ Service: Roots by Hair Stylist-ServicingTime with Tyrah Teopista ¦ ¦ To reschedule, simply reply to this | PAST APPOINTMENT - client told 'confirmed' after it happened
2026-08-01 04:37:53 | 35679362505 | 2026-07-25 | Hi Armando, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 14:45 ¦ Service: Sports Therapy single session (20 min) with Stephen Moghrabi ¦ ¦ To reschedule, simply reply | PAST APPOINTMENT - client told 'confirmed' after it happened

## Never Delivered
Attempted (UTC) | Client number | Message | Why
2026-07-31 15:48:19 | 9207630166 | Hi Abhina, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 22/08/2026 ¦ Time: 11:45 ¦ Service: Hair Loss Consultation with Lawrence Calleja ¦ ¦ To reschedule, simply reply to this message. ¦ | WhatsApp gateway error - message never reached the client
2026-08-01 00:11:52 | 7919061848 | Hi Sisi, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 25/07/2026 ¦ Time: 11:45 ¦ Service: Waxing - Brazillian with Jessica Casha ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee M | WhatsApp gateway error - message never reached the client
2026-08-01 04:55:54 | 35679902579 | Hi Marija, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 31/07/2026 ¦ Time: 15:30 ¦ Service: Roots by Hair Stylist-ServicingTime with Naya Bezzina ¦ ¦ To reschedule, simply reply to this m | WhatsApp gateway error - message never reached the client
2026-08-01 05:16:02 | 35699852836 | Hi Jessica, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 05/09/2026 ¦ Time: 09:30 ¦ Service: Waxing - Forearms with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply to this messa | WhatsApp gateway error - message never reached the client
2026-08-01 05:18:58 | 35699852836 | Hi Jessica, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 16/09/2026 ¦ Time: 10:45 ¦ Service: Threading Full face with Magda Strus ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee | WhatsApp gateway error - message never reached the client
2026-08-01 05:49:54 | 35679300069 | Hi Doreen, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 02/09/2026 ¦ Time: 10:00 ¦ Service: Phi Brows 1 month Touch Up - by Mehmet with Mehmet Cakir ¦ ¦ To reschedule, simply reply to th | WhatsApp gateway error - message never reached the client
2026-08-01 05:57:05 | 35677693001 | Hi Rachel, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 03/08/2026 ¦ Time: 17:00 ¦ Service: Botox- 50 units with Dr Lana Stojakovic ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niume | WhatsApp gateway error - message never reached the client
2026-08-01 05:59:53 | 35699454253 | Hi Brigitte, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 07/08/2026 ¦ Time: 14:45 ¦ Service: Waxing - Full Leg with Jessica Casha ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niumee | WhatsApp gateway error - message never reached the client
2026-08-01 06:05:03 | 35699261985 | Hi Claire, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 23/10/2026 ¦ Time: 17:30 ¦ Service: Med-aesthetic Consultation with Dr Lana Stojakovic ¦ ¦ To reschedule, simply reply to this mess | WhatsApp gateway error - message never reached the client
2026-08-01 06:08:40 | 35679903999 | Hi Raisa, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 01/08/2026 ¦ Time: 15:30 ¦ Service: Toe reconstruction 1 Toe with Aishah Nabagereka ¦ ¦ To reschedule, simply reply to this message. | WhatsApp gateway error - message never reached the client
2026-08-01 06:21:54 | 35679094158 | Hi Marisa, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 11/08/2026 ¦ Time: 14:45 ¦ Service: Gel polish Mani (Gelish) with Frima Dag-o ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ Niu | WhatsApp gateway error - message never reached the client
2026-08-01 06:26:50 | 35699464046 | Hi Karen, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 22/08/2026 ¦ Time: 08:30 ¦ Service: Waxing - Eyebrow Tidy with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply to this mes | WhatsApp gateway error - message never reached the client
2026-08-01 06:29:31 | 35679613580 | Hi Francesca, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 01/08/2026 ¦ Time: 13:45 ¦ Service: Waxing - Eyebrow Tidy with Jessica Casha ¦ ¦ To reschedule, simply reply to this message. ¦ ¦ N | WhatsApp gateway error - message never reached the client
2026-08-01 06:37:44 | 35679466948 | Hi Laura, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 27/08/2026 ¦ Time: 17:00 ¦ Service: Waxing - Eyebrow Tidy with Marie Antoinette Vassallo ¦ ¦ To reschedule, simply reply to this mes | WhatsApp gateway error - message never reached the client
2026-08-01 06:39:55 | 35679094158 | Hi Marisa, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 20/08/2026 ¦ Time: 17:15 ¦ Service: Gel Polish (feet) Gelish (Soak,Scrub, Gelish) with Nashra Apad ¦ ¦ To reschedule, simply reply | WhatsApp gateway error - message never reached the client
2026-08-01 06:48:19 | 35699250704 | Hi Marika, ¦ ¦ Your booking at Niumee is confirmed. ¦ ¦ Date: 05/09/2026 ¦ Time: 11:15 ¦ Service: Gel polish Mani (Gelish) with Aishah Nabagereka ¦ ¦ To reschedule, simply reply to this message | WhatsApp gateway error - message never reached the client

## Real Client Chats
Time (UTC) | Client | They asked | Nima replied | Escalated
2026-07-31 17:05:08 | 202284470419656 | Thanks but I'm not interested in the hairless treatment | It looks like we don't offer a treatment specifically called "hairless." If you meant a different treatment or need assistance with something else, please let me know! How can I help you today? 😊
2026-07-30 08:43:59 | 275835751792711 | Hi | Hello! I'm Nima, the virtual receptionist at Niumee Medical Aesthetics. How can I help you today? 😊
2026-07-30 09:58:16 | 275835751792711 | What is luminfusion facial | The LuminFusion facial is a luxurious treatment designed for deep hydration and revitalization of the skin. Details: - Duration: 90 minutes - Price: Starting from €105 - Provider: Jessica Casha The next available appointment for the LuminFusion facial is on Friday, 31 July at 08:15. Would you like to book this time? 😊
2026-07-30 08:39:00 | 32865710518324 | Hi nima | Hello! I'm Nima, the virtual receptionist at Niumee Medical Aesthetics. How can I help you today? 😊
2026-07-31 10:32:43 | 35677079785 | can I book hair appointment ? | It seems there isn't a specific service listed as "hair appointment." Could you please clarify if you're looking for a particular treatment, such as a haircut, color change, or something else? Let me know the specific service you're interested in! 😊
2026-07-31 10:33:10 | 35677079785 | hair roots | I found the following services for hair roots: 1. Roots Colour - by Director - Price: starting from €42 - Duration: 90 minutes 2. Roots Colour - by Hair Stylist - Price: starting from €42 - Duration: 90 minutes Please let me know which option you'd like to book, and do you have a preferred date and time? 😊
2026-07-31 10:33:19 | 35677079785 | with Jan | It appears that there's still no specific service listed as "hair appointment" with Jan. Could you please clarify if you mean a haircut, color, or another specific treatment? I’ll help you book the right appointment once I have the details! 😊
2026-07-31 10:33:57 | 35677079785 | on 5th August | Could you please clarify which specific service you're looking to book for August 5th? Are you interested in a haircut, hair coloring, or something else? Once I have that detail, I can check availability with Jan for you! 😊
2026-07-31 10:34:15 | 35677079785 | hair roots color | It looks like there isn't a specific service listed as "hair roots color." Could you please provide a bit more detail? Are you looking for a specific hair coloring service, or perhaps a color touch-up? Once I have that information, I can assist you further! 😊
2026-07-31 10:36:06 | 35677079785 | I want roots color with Jan on 5th August | Here are the available options for your roots color appointment with Jan on August 5th: 1) Roots Colour - by Director (90 min) 2) Roots Colour - by Hair Stylist (90 min) Could you please reply with just the NUMBER of the option you'd like to book? 😊
2026-07-31 10:36:14 | 35677079785 | hair stylist | I have confirmed the following available times for your roots color appointment with Jan on August 5th: - 11:15 - 11:30 - 14:00 - 14:15 - 14:30 Please let me know which time works best for you! 😊
2026-07-31 11:49:44 | 35677079785 | 14:00 | I have the available times for your roots color appointment with Jan on August 5th: - 11:15 - 11:30 - 14:00 - 14:15 - 14:30 Could you please let me know which time works best for you? 😊 Additionally, the price for the Roots Colour service will need to be confirmed by our team. 😊
2026-07-31 11:50:50 | 35677079785 | at 14:00 | Your appointment for roots color with Jan on August 5th at 14:00 is confirmed! Before we finalize, please provide your email address for the deposit payment link. The deposit must be paid within 24 hours to secure your appointment. Let me know if you need any further assistance! 😊 | Yes
2026-07-31 11:52:01 | 35677079785 | nensy. smile@gmail.com | Thank you for providing your email, Nevena! Your hair roots color appointment with Jan on August 5th at 14:00 is confirmed. The reception team will email you a secure payment link for the deposit shortly. Please remember that the deposit must be paid within 24 hours to secure your appointment. If you have any other questions or need further assistance, feel free to ask! 😊 | Yes
2026-07-31 15:37:04 | 35699017313 | Thank you | Thank you for reaching out, Julia! The next available appointment for a Hair Loss Consultation with Lawrence Calleja is on August 20, 2026, at the following times: - 19:00 - 19:15 Please let me know which time works best for you! 😊
2026-07-31 17:04:59 | 35699017313 | Thanks but I'm not interested in the hairless treatment | Hello Julia! I'm Nima, the virtual receptionist at Niumee Medical Aesthetics. I understand you're not interested in hair loss treatment. If there's something else you would like to inquire about or book, just let me know how I can assist you today! 😊
2026-07-31 18:02:41 | 35699292900 | Ok | Hello! This is Nima from Niumee Medical Aesthetics. I see you might be referring to your recent booking confirmation. Could you please confirm what details you would like to discuss or if you have any specific questions?
2026-07-31 18:03:08 | 35699292900 | Yes confirmed | The next available slot for the Hair Loss Consultation with Lawrence Calleja is on Wednesday, August 20, 2026. Here are the available times: - 19:00 - 19:15 Please let me know which time works best for you! 😊
2026-07-31 23:37:58 | 35699467286 | Thank you for your enquiry. For therapy and/ or assessment enquiries please use the form on our website which can be found here: https://talkingtherapyteam.com/#booking When using this form, please provide as much of the following information as possible: - the service you require (e.g. therapy o | Bongu, Emma! Jiena Nima, il-receptionist virtuali hawnhekk fil-Niumee Medical Aesthetics. Grazzi talli kont fil-kuntatt ma 'l-aqwa tamiet tagħna. Minħabba li kont int bagħt t-tweġiba tiegħek dwar it-talba li għamilt, trid tikkonferma xi ħaġa oħra? Kif nista' ngħinek illum? 😊
2026-07-31 17:56:36 | 35699479623 | Thanks | Hi Jeanette, thank you for getting in touch! The next available slot for the Hair Loss Consultation with Lawrence Calleja is on **August 20, 2026**, at the following times: - 19:00 - 19:15 Please let me know which time works best for you! 😊
2026-07-31 17:58:10 | 35699479623 | I didnt apply for hair loss 😅 | Thanks for clarifying, Jeanette! Could you let me know which service you're interested in? Once you specify that, I can help you with the next steps. 😊

## Findings and Actions
# | Finding | Action | Priority
1 | Nima cannot send or receive. WhatsApp device disconnected 1 Aug 04:37 (401, device_removed). | Find out if someone at Niumee unlinked it. Rescan QR on the Niumee phone. Until then the assistant is invisible to clients. | NOW
2 | 62 clients hold a booking confirmation; reschedules were never sent, so an unknown number are now wrong. | Cross-check each against their current Zenoti appointment and give reception only the ones that actually differ. | NOW
3 | 19 clients were told an appointment was confirmed AFTER it had already taken place. | Add a date sanity check: never confirm an appointment in the past. Likely caused by reception logging walk-ins retroactively. | Before card goes back on
4 | Confirmation card ignored 272 reschedule/cancel/status events. | Handle Updated, Rescheduled and Cancelled events, not just Created. | Before card goes back on
5 | A client replying to a confirmation reached an assistant with no idea what her booking was, and it invented a service (Jeanette - offered a Hair Loss Consultation she never asked for). | Pass the real service into the client context. Where the service is unknown the assistant must ask, never guess. Remove 'reply to reschedule' until the reply path works. | Before card goes back on
6 | Live assistant was down 2h49m on 30 Jul after code was deployed straight to live without being run once. | No workflow goes live until it has executed at least once under our control. Add syntax validation and an automatic health alarm. | Standard, before any new feature
7 | Assistant failed to understand a real client's natural wording six times in a row ('hair appointment', 'hair roots', 'with Jan', 'hair roots color') before finding the service. | Broaden matching for hair-salon phrasing. She persisted, most clients would not. | High
8 | Same conversation: assistant quoted the price at EUR42, then later said the price 'needs to be confirmed by our team'. | Contradiction within one conversation. Once a price is quoted from the catalogue it must not be walked back. | High
9 | Same conversation: assistant addressed the client as 'Nevena', which is a Niumee laser practitioner, not the client. | Never infer a client's name from an email address or staff list. Use the name they gave or none. | High
10 | Client said '14:00'; assistant re-listed the same times instead of accepting it. She had to repeat 'at 14:00'. | Accept a bare time as a selection when it matches an offered slot. | Medium
11 | WF-MissedCall Poller v2 ran 2,901 times in 48h, about once a minute, and its own name says it should not be active yet. | Review whether it should be running at all. It is 67% of all executions on the instance. | Medium